## Sheet1
Task | Goal | Tools | Duration | Deliverable
Automated Discovery of Infra/Apps | Baseline all systems & dependencies | Flexera / Live Optics / RVTools | 2 days | Inventory & usage heatmaps
Software License & Compliance Audit | Identify over-/under-licensing | Flexera FNMS / Snow / SCCM | 2 days | Compliance report
TCO Modeling & Cloud Suitability | Compare on-prem vs. cloud costs | Flexera CloudScape / AWS Migration Evaluator | 2 days | 3- and 5-year TCO charts
Risk & Vulnerability Assessment | Surface security gaps & EOL issues | Qualys / Nessus / Flexera Secunia | 2 days | Risk matrix & remediation list