## Sheet1
Task | Goal | Tools | Duration | Deliverable
Review biz ops & tech environment | Understand current environment | Workshops, Interviews, Excel | 2 days | Current state analysis doc
Build infra/app inventory | Document assets & deps | Flexera/Live Optics/RVTools | 3 days | Asset & dependency matrix
Networking & connectivity review | Assess readiness | Nmap, NetFlow, Visio | 2 days | Connectivity assessment report
Performance, security, storage review | Evaluate NFRs | Zabbix, SolarWinds | 2 days | NFR evaluation checklist
Review emerging-tech use cases | Understand future needs | Workshops, Gartner reports | 1 day | Emerging tech matrix
Design cloud architecture & networking | Blueprint target state | Lucidchart, Terraform | 3 days | Cloud target architecture
Define DevOps, monitoring & logging policies | Standardize ops best practices | Grafana, Prometheus, ELK | 2 days | DevOps & Observability policies
Cost analysis & comparison | Support budget planning | Flexera CloudScape, Excel | 2 days | TCO comparison report